## Sheet1
Date( mm/dd/yyyy) | Task Name | Resource Name(s) RaviRanjan Pandey | Resource Name(s) Madhu Sudhan | Resource Name(s) Arfaat Kirkire | Resource Name(s) Shalini Gupta | Author (of Item for follow-on questions) | Is it ready for Demo?
25/04/2017 | Build Hybris Commerce Suite (6.0) | Installed the Hybris Commerce Suite and the desired application(B2B) | Installed the Hybris Commerce Suite and the desired application(B2B) | Installed the Hybris Commerce Suite and the desired application(B2B) | Installed the Hybris Commerce Suite and the desired application(B2B) | Gyaneshwar dubey | Yes
26/04/2017 | Custom store Setup | eeyewear custom store was set up | eeyewear custom store was set up | eeyewear custom store was set up | eeyewear custom store was set up | Gyaneshwar dubey | Yes
27/04/2017 | eeyewear Site Setup | Reviewed the core system setup modified the initial system setup and started working with impexes | Reviewed the core system setup modified the initial system setup and started working with impexes | Reviewed the core system setup modified the initial system setup and started working with impexes | Reviewed the core system setup modified the initial system setup and started working with impexes | Gyaneshwar dubey | Yes
2016-10-13 | Creating eeyewear store(core data) | Changed the Core data impex files . | Changed the Core data impex files . | Changed the Core data impex files . | Changed the Core data impex files . | Gyaneshwar dubey | Yes
2017-04-05 | Creating eeyewear store(sample data) | Worked with categories,product,product prices,product stocklevels impex files. | Worked with categories,product,product prices,product stocklevels impex files. | Worked with localization, suppliers and warehouses impex files. | Worked with localization, suppliers and warehouses impex files. | Gyaneshwar dubey | Yes
2017-05-05 | Creating eeyewear store(sample data) | Worked with categories,product,product prices,product stocklevels impex files. | Worked with categories,product,product prices,product stocklevels impex files. | Worked with localization, suppliers and warehouses impex files. | Worked with localization, suppliers and warehouses impex files. | Gyaneshwar dubey | Yes
2017-08-05 | Cms-content.impex | Worked on cms-content.impex and cms-content_en.impex files. | Worked on cms-content.impex and cms-content_en.impex files. | Worked with categories,product,product prices,product stocklevels impex files. | Worked with categories,product,product prices,product stocklevels impex files. | Gyaneshwar dubey | Yes
2017-09-05 | Cms-content.impex | Worked on cms-content.impex and cms-content_en.impex files. | Worked on cms-content.impex and cms-content_en.impex files. | Worked on cms-content.impex and cms-content_en.impex files. | Worked on cms-content.impex and cms-content_en.impex files. | Gyaneshwar dubey | Yes
2017-10-05 | Products in Product Cockpit | Worked with the sample data afiles and the products were visible in the product cockpit and the site was up. | Worked with the sample data afiles and the products were visible in the product cockpit and the site was up. | Worked with the sample data afiles and the products were visible in the product cockpit and the site was up. | Worked with the sample data afiles and the products were visible in the product cockpit and the site was up. | Gyaneshwar dubey | Yes
2017-11-05 | Functionality of the eeyewear store | Checked if the site was running succesfully and the checkout was happening properly. | Checked if the site was running succesfully and the checkout was happening properly. | Checked if the site was running succesfully and the checkout was happening properly. | Checked if the site was running succesfully and the checkout was happening properly. | Gyaneshwar dubey | Yes
2017-12-05 | Early Login | Installed Secureportal addon, changed the project.properties file and updated the system.The custom website was working with early login. | Planned Leave | Installed Secureportal addon, changed the project.properties file and updated the system.The custom website was working with early login. | Installed Secureportal addon, changed the project.properties file and updated the system.The custom website was working with early login. | Gyaneshwar dubey | Yes
15/5/2017 | Setup of Variant Products and defining Promotions. | Worked on Variants . | Planned Leave | Worked on Variants . | Worked on Variants . | Gyaneshwar dubey | Yes
16/5/2017 | Setup of Variant Products and defining Promotions. | Worked on Variants and the product images . | Planned Leave | Worked on Variants and the product images . | Worked on Variants and the product images . | Gyaneshwar dubey | Yes
17/5/2017 | Coupons | Worked on Serial voucher. | Planned Leave | Worked on Serial voucher. | Worked on Serial voucher. | Gyaneshwar dubey | Yes
18/5/2017 | Coupons and Coming soon. | Worked on Serial voucher.Coming soon funtionality was implemented. | Planned Leave | Worked on Serial voucher.Coming soon funtionality was implemented. | Worked on Serial voucher.Coming soon funtionality was implemented. | Gyaneshwar dubey | Yes
19/5/2017 | Customization of PDP | Created the PDP attributes under Product type and newa attributes were added. | Planned Leave | Created the PDP attributes under Product type and newa attributes were added. | Created the PDP attributes under Product type and newa attributes were added. | Gyaneshwar dubey | Yes
22/5/2017 | Customization of Product Cockpit with new PDP attributes | Implemented the customization of product cockpit with new PDP attributes. | Planned Leave | Implemented the customization of product cockpit with new PDP attributes. | Implemented the customization of product cockpit with new PDP attributes. | Gyaneshwar dubey | Yes
23/5/2017 | Hot folder | Completed | Planned Leave | Completed | Completed | Gyaneshwar dubey | Yes
24/5/2017 | WCMS cockpit | Completed | Planned Leave | Completed | Completed | Gyaneshwar dubey | Yes
25/5/2017 | RegistrationPage | Completed | Completed | Completed | Completed | Gyaneshwar dubey | Yes
26/5/2017 | myAccount Update | Completed | Completed | Completed | Completed | Gyaneshwar dubey | Yes
29/5/2017 | Pickup in store | Completed | Completed | Completed | Completed | Gyaneshwar dubey | Yes
29/5/2017 | Shipping Method | Completed | Completed | Completed | Completed | Gyaneshwar dubey | Yes
29/5/2017 | Quick Order | Completed | Completed | Completed | Completed | Gyaneshwar dubey | Yes
30/5/2017 | Quotes | Completed | Completed | Completed | Completed | Gyaneshwar dubey | Yes
31/5/2017 | Documentation | Completed | Completed | Completed | Completed | Gyaneshwar dubey | Yes
2017-01-06 | Demo | Completed the POC | Completed the POC | Completed the POC | Completed the POC | Gyaneshwar dubey | Yes